## Dashboard
Project Name: Project Plan
Description: Google Project Management
Owner: David Udoh
Status: Active
Key Docs | Description
Project charter | https://docs.google.com/document/d/1jjR77UV83sCOTMLhhtFkbAibua0o2OBDNKhm-uyJl0s/edit
Statement of work | https://docs.google.com/document/d/1xnrCRTYOunDwIhMHMyXFeK2cAcM_I1nuKstssyeQQ7I/edit#heading=h.twagzrt4oci8
Risk Management Plan | https://docs.google.com/document/d/1gi8wc8B_W0PCzmZmjC10vNZgAqHr9sBxgUTyYNpy36c/edit#heading=h.koqp1zr190fb
Schedule | https://docs.google.com/spreadsheets/d/1HtndwmqbobFOA5MBspfsLmtoj7tXrLJtPW2AretXmrM/edit#gid=200431927
Budget | https://docs.google.com/spreadsheets/d/1HtndwmqbobFOA5MBspfsLmtoj7tXrLJtPW2AretXmrM/edit#gid=1159596562
Communication plan | https://docs.google.com/spreadsheets/d/1NcfSawxsyGEYPk1qil88SHV5LJ0B6y3Suh8gXzAIafo/edit#gid=1111153036
Shared folder
RACI chart | https://docs.google.com/spreadsheets/d/1SVIOcyWW3qCRz0nlThlUk05fBztfj5JZwZrsA_0G8nQ/edit#gid=479253282

## Project Schedule
Gantt Chart
TITLE: Plant Pals Operations and Training Plan | [6 empty] | COMPANY NAME: |  |  |  |  | Office Green
PROJECT MANAGER: DAVID UDOH | [6 empty] | CREATION DATE: |  |  |  |  | 19/4
TASK ID NUMBER | MILESTONES & TASKS | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [29 empty] | PHASE TWO | [14 empty] | PHASE THREE
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[7 empty] | MARCH | [22 empty] | APRIL | [21 empty] | MAY | [20 empty] | JUNE
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Establish a plant delivery and logistics plan | [5 empty] | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11
1.1 | Source packaging materials | Fulfillment Director | 3/1 | 3/12 | 10 | 0% | bar: MARCH M 1 to MARCH F 12
1.2 | Hire delivery drivers | Human resource specialist | 3/15 | 3/26 | 10 | 0% | bar: MARCH M 15 to MARCH F 26
1.3 | Calculate delivery fees | Financial analyst | 3/29 | 4/9 | 10 | 0% | bar: MARCH M 29 to APRIL F 9
2 | Select and install supply chain software and equipment
2.1 | Supervise vendor setup of inventory management and fulfillment software | Inventory Manager | 4/12 | 4/14 | 3 | 0% | bar: APRIL M 12 to APRIL W 14
2.2 | Supervise vendor installation of the fulfilment equipment | Inventory Manager | 4/15 | 4/16 | 2 | 0% | bar: APRIL R 15 to APRIL F 16
2.3 | Determine internal safety protocols for the equipment | Quality assurance tester | 4/19 | 4/30 | 10 | 0% | bar: APRIL M 19 to APRIL F 30
3 | Develop and launch an employee training program
3.1 | Develop training sessions | Human resource specialist | 5/3 | 5/14 | 10 | 0% | bar: MAY M 3 to MAY F 14
3.2 | Train employees to use the software and equipment | Training Manager | 5/17 | 5/28 | 10 | 0% | bar: MAY M 17 to MAY F 28
3.3 | Monitor employee progress and improve training process | Training Manager | 5/31 | 6/11 | 10 | 0% | bar: MAY M 31 to JUNE F 11

## RACI Chart
R - Responsible | Completes the deliverable or task.
A - Accountable | Makes final decisions and signs off on task completion. Only 1 per task.
C - Consulted | An advisor, stakeholder, or subject matter expert who offers guidance before an action is taken.
I - Informed | Kept up to date on decisions made.
Plant Pals Marketing & Sales Strategy | Director of product | Marketing manager | Marketing coordinator | Head of sales | Copywriter | Sales manager
PHASE 1
Task/Deliverable
Create a marketing plan for the new service | I | A | R | C | C
Write promotional copy | I | I | A | C | R
Design marketing assets (e.g., flyers, brochures, and online advertisements) | C |  | A | C | R
Create a customer outreach and onboarding plan | C |  |  | A |  | R

## Budget
Budget: Project Plant Pals Operations & Training
[7 empty] | TARGET BUDGET | ACTUAL/ FINAL SPEND | UNDER/ OVER
Activity Template: Project plan | [6 empty] | 60800 | 0 | 60800
| LABOR |  |  | MATERIALS |  | FIXED COST | BUDGET | ACTUAL | UNDER/OVER
MILESTONES & TASKS | EMPLOYEE DETAILS | HOURS | RATE | UNITS | $/UNIT
Milestone 1: Establish a plant delivery and logistics plan
Task 1: Purchase delivery trucks |  |  |  | 2 | 15000 |  | 30000 |  | -30000
Task 2: Source packaging materials |  |  |  | 1500 | 2 |  | 3000 |  | -3000
Task 3: Pay delivery drivers | 2 delivery drivers | 80 | 15 |  |  |  | 1200 |  | -1200
-- | [5 empty] | Total | 34200 | 0
Milestone 2: Select and install supply chain management software and equipment
Task 1: Source vendor | [5 empty] | 15000 | 15000 |  | -15000
-- | [5 empty] | Total | 15000 | 0
Milestone 3: Develop and launch an employee training program
Task 1: Develop training sessions | HR Specialist | 80 | 50 |  |  |  | 4000 |  | -4000
Task 2: Train employees to use the software and equipment | Training manager | 80 | 25 |  |  |  | 2000 |  | -2000
Task 3: Monitor employee progress and improve training processes | Training manager | 80 | 25 |  |  |  | 2000 |  | -2000
-- | [5 empty] | Total | 8000 | 0
Reserve buffer | [6 empty] | 3600
TOTAL | [6 empty] | 60800 | 0

## Copy of Comm Plan Template
Project Plant Pals: Employee Training Communication Plan
Recipients | Type of Communication | Frequency | Sender/Owner | Key Dates | Delivery Method | Goal | Resource Links | Notes
Core Team | Planning Meeting | Daily | Project Manager | Every day at 3pm | In Person | Project planning and task updates to make sure the team stays on track | [link to meeting agenda and notes] | If needed, check in with manager about any high-level questions before meetings.
Software and Equipment Vendor | Planning Meeting | One time | Core Team: HR Specialist | One time 9am | In Person | Go over the training manual in order to create an effective training plan for Office Green's employees |  | he would be assisted by the training manager
Human Resources | Status Update | Daily | Core Team: HR Specialist | everyday at 9am | In Person | Project planning assistance; provide support during the training session |  | this is critical to the overall event happening
Facilities | Planning Check-In | One time | Core Team: Administrative Coordinator | 2 days before training | Phone Call | Reserve rooms, spaces, and equipment needed for employee training
Print Shop | Status Update | Daily | Core Team: Training Manager | Everyday at 8am | Phone Call | Coordinate on the printing and delivery of training manuals for employees |  | he would be highly assisted by the HR specialist
Office Green employees | Informational Update | One time | Core Team: HR Specialist | 2 days before training | Email (from company address) | Communicate schedules, locations, and other necessary details to trainees
Office Green employees | Training | Daily | Core Team: Training Manager | Everyday at 9am | In Person | Train employees to use the supply chain management software and equipment |  | mostly until everyone on board can operate effectively
Office Green employees | Survey | One time | Core Team: Training Manager | last day of training 4pm | Email (from individual address) | Post-training survey |  | sometimes everyday after training to not miss any drawback
Your Manager | Status Update | Weekly | Project Manager | 12am every monday | In Person | Update on event planning, ask questions, and get feedback |  | can do phonecall if in person not feasible
Senior Leaders: Director of Operations and the Director of Product (and CC your manager) | Status Update | Weekly | Project Manager | 9am every friday | Email (from individual address) | High-level information and general updates